## Schedule
Project schedule and Gantt template
Example data. Replace the amber inputs. Calendar days include both start and finish. Tasks do not reschedule automatically.
Timeline starts |  | 2026-11-09T00:00:00.000Z
20 calendar days shown. Change the timeline start to view another period. Green cells mark the planned task dates.
Task / deliverable | Owner | Start | Finish | Days | Status | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28
Confirm the client brief | Maya | 2026-11-09T00:00:00.000Z | 2026-11-10T00:00:00.000Z | 2 | Complete
Prepare the first draft | Arun | 2026-11-11T00:00:00.000Z | 2026-11-13T00:00:00.000Z | 3 | In progress
Review the draft | Leena | 2026-11-14T00:00:00.000Z | 2026-11-16T00:00:00.000Z | 3 | Not started
Resolve review queries | Arun | 2026-11-17T00:00:00.000Z | 2026-11-18T00:00:00.000Z | 2 | Not started
Confirm client approval | Maya | 2026-11-19T00:00:00.000Z | 2026-11-20T00:00:00.000Z | 2 | Not started
Complete the handoff | Leena | 2026-11-21T00:00:00.000Z | 2026-11-23T00:00:00.000Z | 3 | Not started

## Burndown
Burndown chart example
Fictional example. Enter remaining work once daily in column C. Leave unobserved days blank. Use one unit throughout.
Starting points | 40
Planning intervals | 10
Day | Ideal remaining | Actual remaining | Note / scope change
0 | 40 | 40
1 | 36 | 40
2 | 32 | 36
3 | 28 | 33
4 | 24 | 28
5 | 20 | 28 | Review work waiting
6 | 16 | 21
7 | 12 | 16
8 | 8
9 | 4
10 | 0